## Sheet1
Budget Estimate - Implementation of the ILO Solution
Package | Deliverable/Action | Mandays in total | Price per manhour | 20
Project Initiation |  |  | Price per manday | 160
Project kick-off, establishment of the project team, project office etc. |  | 20 | Project management % | 0.3
Training (incoming) of the supplier's personnel by ILO (5 people) |  | 25
Requirements gathering and Business process reengineering required to exchange the data sets necessary for the Slot 1, including appropriate documentation
| Analysis of the 30 KILM data sources including documentation | 90
| Design of the interfaces and processes in the source institutions | 90
All necessary code, installation packages, scripts and other binaries necessary to be installed on MoL and other institutions’ systems
| Preparation of the development and test infrastructure | 10
| Development of the 30 interfaces | 210
| Testing of the interfaces | 60
| Installation packages | 5
All necessary tests of the system signed-off by the MoL representatives |  | 20
Trainings for the users of the LMIS.Stat and for the personnel operating the distributed solution |  | 15
Deployment of the solution on MoL and other institutions | Including negotiations on the infrastructure modifications | 25
Quality Management (documentation meeting standards described in the Conceptual Framework) |  | 20
Operations Support, Maintenance and Warranty |  | 50
Project Management |  | 192
Total |  | 832
Total in JOD |  | 133120