## Communication Action Plan
Skills for Employment and Social Inclusion Programme
Action Plan
Draft 2018
Communication and Visibility Campaing
Plan of work | Details of proposed action | Indicators of achievement and sources of verification | Incharge | Estimated Budget | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01
Activites
Action 1. Encourage trainers of vocational training providers to enrol in the VET e-platform | Conduct minimum four awareness sessions to prompt the importance of the e-platforms. , Google ads to promote and spread the word of the e-platform | • Post survey to measure the impact of the awareness session • Number of registired trainers after each awareness session (quantitative data) • Number of clicks on the google ad | WG2 / Comm expert for visibility and media coverage | 18,000 Euros | bar: 2019-02-01 to 2019-06-01
Action 2. Encourage graduating students to seek advice and support from employment services programmes for their activation in the labour market and from microfinance for self-employment with particular focus on disadvantaged and groups with special needs | Open Week for students to meet specialized services providers and to seek advice | • Media coverage report • Photos report | Comm expert / WG4 | 10,000 Euros | bar: 2019-02-01; 2019-06-01
Action 3. Promote the results of Accreditation and QA of TVET providers, Recognition of Prior Learning and TVET qualification registered in the TVQF | Produce TV commercial ad about the porject and the benefits of registering in the TVQF to be broadcasted at 2 local TV station (40 airing times during 7 days). | • Infographics to show how many person the TV commercial reached after each airing time • Number of visits to the website after the airing time (quantitative data) | Comm expert with inputs from WG1,2,3,& 4. | 40,000 Euros | bar: 2018-12-01 to 2019-02-01
Action 4. Highlight and disseminate increased access to Vocational Training institutions, including Centres of Excellence, equipped and refurbished in line with the programmes based on qualification registered in the TVQF | • Visit the center of excellence to be able to showcase plates that indicates full visual visibility for the European Union. • Run online campaign (Facebook ads) and features stories. • Ensure media coverage by hiring a professional photographer | • Insights (Page likes, views, previews, etc) • photos of the visual identity | Comm expert with inputs from WG2, WG3 | 8,000 Euros | bar: 2018-12-01 to 2019-02-01
Action 5. Activation and empowerment of the beneficiaries thanks to the new regulations of the National Aid Fund (NAF) and through annual Job Fairs. | • Workshops to discuss and spread the new regulations of NAF • Produce flyers and leaflets about the new regulations. • Run Online campaigns to promote the benefits of the activations (google ads) | • Feedback from the workshops • Checking the success of the google ads via CTR (click through rate) | Comm expert / WG4 | 20,000 Euros | bar: 2018-12-01; 2019-02-01; 2019-04-01; 2019-06-01; 2019-08-01
Action 6. The activation and empowerment of the beneficiaries according to the new regulations of the National Aid Fund (NAF) and through annual Job Fairs. | • Run workshops to discuss and spread the new regulations of NAF. • Produce flyers and leaflets about the new regulations. • Run Online campaigns to promote the benefits of the activations (google ads) •Regoinal Job Fair (Aqaba) | • Feedback from the workshops • Checking the success of the google ads via CTR (click through rate) • Job fair survey and media coverage | Comm expert / WG4 | 25,000 Euros | bar: 2019-03-01; 2019-06-01 to 2019-07-01
Action 7. To promote positive social image of TVET, students' self-esteem and appreciation by their families | • A nationwide campaign to raise awareness and promote positive image of TVET which will include - Spreading direct messages to the target groups through one of the telecommunication companies (Zain/Orange) to ensure efficient and effective channeling of information and announcements to the beneficiaries. - Life testimonies to be broadcasted on local radio station (Radio spot). - Animated videos to be broadcasted on local TV. | • Conduct an attitude survey • Number of reached people via telecommunciaton companies • Clicks on the youtube videos | Comm expert with inputs from WG1 | 45,000 Euros | bar: 2019-01-01 to 2019-04-01
Action 8. Promote social inclusion of women, particularly disadvantaged ones and their participation in the labour market through self-employment (cooperative societies), employment paths e.g. nurseries services), support to career building for decent jobs (Indicator 7) | • Conduct a national level event to link community based organizations and disadvantages women and discuss the importance of SI of women in the labor market. • Print and distribute brochures and flyer among beneficiaries. • Encourage and support awareness sessions led by disadvantages women. • Invite the media to ensure coverage of SESIP and EU in the event. | • Media coverage report • Sruvey • Number of the information reached to people | Comm expert / WG4 | 14,000 Euros | bar: 2019-02-01; 2019-04-01; 2019-06-01
Communcation Expert
Activites
Reactivation of the ETVET Council web-portal based on ICT | • Outsource a web developer to design a new website or redesign the current website. • Collect materials for the web site (annual reports, flash reports, publications, hand-outs, manuals, articles, photos, agreement, success stories) • Link with the other online tools and collaboration platforms supported by TA SESIP such as M&E IT application, the LMIS Portal, , Donor Coordination, eLearning platform • Establishment of Facebook page promote the overall project activities including the revised ETVET legal, regulatory and policy framework and the achievements of the E-TVET sectors supported by the actions under the EU financial agreement. • Creation of TA SESIP complaints and questions line. | • Number of visitors, Avrage time on page, calls to action, bounce rat, etc. | Comm expert/ Ayman/ with inputs from WG1,2,3 and 4 | 10,000 Euros | bar: 2018-12-01 to 2019-09-01
Support the TA Project Components (1-4) on the implementation of the CS, AP and Actions | Bi-weekly meetings | • Reports | Comm expert | N/A | bar: 2018-12-01 to 2019-09-01
Follow up and support to local partners and communication companies involved in implementing the TA project's CVC in Jordan | Monthly visits to ensure the correct implementation of the project | • Reports | Comm expert | N/A | bar: 2018-12-01 to 2019-09-01
Improve the image of the ETVET | Launch awarness campaign to improve the image of ETEVT and to link it to labour market before the start of the acadimic year (3 short videos and paid online campain (youtube and facebook ads) | • checking the success of the google ads via CTR (click through rate)/ | Comm expert with inputs from WGs' | 20,000 Euros | bar: 2019-02-01 to 2019-03-01; 2019-07-01 to 2019-09-01
| Produce photo bank through hiring a talented photographer to take shots of careers/jobs related to our project and post it on website and over social media platforms | • Website traffice and views | Comm expert with inputs from WGs' | 6,000 Euros | bar: 2019-02-01 to 2019-04-01
| Produce flyers and banners, roll ups, folders, usb, pins, note-pads, etc) | N/A | Comm expert with inputs from WGs' | 30,000 Euros | bar: 2019-01-01 to 2019-02-01
| Develop ETVET Success stories booklet | N/A | Comm expert with inputs from WGs' | 7,000 Euros | bar: 2019-01-01 to 2019-04-01
Outsource the services of a graphic designer | To create a simple, modern, and memorable visual identity (VI) for the SESIP Programme that speaks to the different target groups in Jordan, while reﬂecting the communication objectives and the mandate of the Programme. |  | Comm expert/ GIZ procurement | 15,000 Euros | bar: 2018-12-01 to 2019-01-01
Data Collection | Collection of data and relevant documentations in Jordan for the report on assessment and update of the state of art of communication and visibility in ETVET sector |  | Comm expert with inputs from WGs' | N/A | bar: 2018-12-01 to 2019-09-01
On-line Project newsletter | Capture and document activities, events, conferences, workshops and prepare content for the newsletter. Mention media coverage, challenges, and good practices. |  | Comm expert with input from WG1,2,3 and 4 | 0 | bar: 2019-01-01; 2019-03-01; 2019-05-01; 2019-07-01; 2019-09-01